## A3Template
A3 Template
Project Information
Project Title:
Sponsor(s):
Leader(s):
Team Member(s):
(Click the + / - button to the left to expand / collapse the section.)
Problem
Describe the issue in 1 or 2 sentences. Just state the problem(s), not any goal or implied solution.
(Click the + / - button to the left to expand / collapse the section.)
Background
Provide background information to describe why the issue is important and why the team should work on it in 1-4 sentences. Who is impacted by the problem? How does the problem negatively impact them? How does the project align with organizational objective?
(Click the + / - button to the left to expand / collapse the section.)
Current Condition
Describe in a few bullet points what the current conditions look like, or you can draw a diagram to create a high-level flow chart.
(Click the + / - button to the left to expand / collapse the section.)
AIM / Target / Specific Outcome
Write a SMART goal here. (Specific, Measurable, Achievable, Relevant, Time-Based)
(Click the + / - button to the left to expand / collapse the section.)
Problem Analysis
List the main problem(s). Ask appropriate “Why?” questions until you reach the root cause. A rule-of-thumb: you haven’t reached the root cause until you’ve asked “Why?” at least 5 times. List the answer to each “Why?” question. A fishbone diagram or Pareto chart might be useful.
Main Problem |  | Why?
(Click the + / - button to the left to expand / collapse the section.)
Recommended Changes / Countermeasures
List recommended changes.
(Click the + / - button to the left to expand / collapse the section.)
Implementation Plan
List the change(s) you will make (“What”), “Who” is responsible for guiding the change, “When” the change will occur, and the “Anticipated Outcome” the change should deliver.
What | Who | When | Anticipated Outcome
(Click the + / - button to the left to expand / collapse the section.)
Follow Up
How will you measure improvement?
Key Performance Indicator |  | How will you measure it?
(Click the + / - button to the left to expand / collapse the section.)

## WBS-CapstoneList
Steps to create a Work Breakdown Structure List and Diagram
Step 1: | List your deliverables in separate cells in Row 13 in the Project section starting in column A. Insert more columns after the last deliverable if you need more space.
Step 2: | List the tasks that need to be completed under each deliverable.
Step 3: | Increase the indent on tasks and subtasks. (It makes the lists easier to read.)
Step 4: | Copy the lists of Deliverables and Tasks and paste them in the name column in the Task List section. (You want to create a single column that lists all the deliverables and tasks.)
Step 5: | Give each Deliverable and Task a unique ID number.
Step 6: | Label each Deliverable, Task, and Subtask with the correct type in the type column.
Step 7: | Indicate which deliverables belong to the project, which tasks belong to which deliverable, and which subtasks belong to which task by providing the correct ID for each in the dependent column. See the example below.
Step 8: | Copy the information in the 5 columns of the Task List section WITHOUT THE HEADERS and paste it into the table on the left side of the WBS-Chart sheet. (DON'T PASTE OVER THE HEADERS IN THAT SHEET. THE CHART WON'T WORK IF YOU DO.)
Step 9: | Click Refresh in the top-left corner of the chart. You should see a WBS diagram for your project.
Capstone |  |  |  | Task List
Project Proposal | Practicum Project | Final Paper | Final Presentation | id | name | type | dependent | blank
Site Selection | Objective 1 | Paper introduction part 1 | Draft slide deck for presentation | 0 | Capstone | Overview
Site Training & Preparation | Objective 2 | Paper introduction part 2 | Oral presentation day | 1 | Project Proposal | Deliverable | 0
Initial Understanding | Objective 3 | Paper methods part 1 | Final poster | 2 | Site Selection | Task | 1
Project Kickoff Meeting |  | Paper methods part 2 |  | 3 | Site Training & Preparation | Task | 1
A3 Template |  | Paper methods part 3 |  | 4 | Initial Understanding | Task | 1
Monitoring & Reporting |  | Paper results |  | 5 | Project Kickoff Meeting | Sub-task | 4
Closer Review |  | Paper discussion & conclusion |  | 6 | A3 Template | Sub-task | 4
Problem Statement |  | Full draft of paper and abstract |  | 7 | Monitoring & Reporting | Sub-task | 4
Literature Search |  | Review by Assistant Dean |  | 8 | Closer Review | Task | 1
Specific Aim & Objectives |  | Review by Associate Dean |  | 9 | Problem Statement | Sub-task | 8
Context |  |  |  | 10 | Literature Search | Sub-task | 8
Framework |  |  |  | 11 | Specific Aim & Objectives | Sub-task | 8
Methods & Deliverables |  |  |  | 12 | Context | Sub-task | 8
Instruments |  |  |  | 13 | Framework | Sub-task | 8
Work Breakdown Structure |  |  |  | 14 | Methods & Deliverables | Sub-task | 8
Project Timeline |  |  |  | 15 | Instruments | Sub-task | 8
Proposal Submission |  |  |  | 16 | Work Breakdown Structure | Sub-task | 8
Proposal Approval |  |  |  | 17 | Project Timeline | Sub-task | 8
|  |  |  | 18 | Proposal Submission | Sub-task | 8
|  |  |  | 19 | Proposal Approval | Sub-task | 8
|  |  |  | 20 | Practicum Project | Deliverable | 0
|  |  |  | 21 | Objective 1 | Task | 20
|  |  |  | 22 | Objective 2 | Task | 20
|  |  |  | 23 | Objective 3 | Task | 20
|  |  |  | 24 | Final Paper | Deliverable | 0
|  |  |  | 25 | Paper introduction part 1 | Task | 24
|  |  |  | 26 | Paper introduction part 2 | Task | 24
|  |  |  | 27 | Paper methods part 1 | Task | 24
|  |  |  | 28 | Paper methods part 2 | Task | 24
|  |  |  | 29 | Paper methods part 3 | Task | 24
|  |  |  | 30 | Paper results | Task | 24
|  |  |  | 31 | Paper discussion & conclusion | Task | 24
|  |  |  | 32 | Full draft of paper and abstract | Task | 24
|  |  |  | 33 | Review by Assistant Dean | Task | 24
|  |  |  | 34 | Review by Associate Dean | Task | 24
|  |  |  | 35 | Final Presentation | Deliverable | 0
|  |  |  | 36 | Draft slide deck for presentation | Task | 35
|  |  |  | 37 | Oral presentation day | Task | 35
|  |  |  | 38 | Final poster | Task | 35

## WBS-CapDiagram
Employee ID | Name | Title | Manager ID | Role Type
0 | Capstone | Overview
1 | Project Proposal | Deliverable | 0
2 | Site Selection | Task | 1
3 | Site Training & Preparation | Task | 1
4 | Initial Understanding | Task | 1
5 | Project Kickoff Meeting | Sub-task | 4
6 | A3 Template | Sub-task | 4
7 | Monitoring & Reporting | Sub-task | 4
8 | Closer Review | Task | 1
9 | Problem Statement | Sub-task | 8
10 | Literature Search | Sub-task | 8
11 | Specific Aim & Objectives | Sub-task | 8
12 | Context | Sub-task | 8
13 | Framework | Sub-task | 8
14 | Methods & Deliverables | Sub-task | 8
15 | Instruments | Sub-task | 8
16 | Work Breakdown Structure | Sub-task | 8
17 | Project Timeline | Sub-task | 8
18 | Proposal Submission | Sub-task | 8
19 | Proposal Approval | Sub-task | 8
20 | Practicum Project | Deliverable | 0
21 | Objective 1 | Task | 20
22 | Objective 2 | Task | 20
23 | Objective 3 | Task | 20
24 | Final Paper | Deliverable | 0
25 | Paper introduction part 1 | Task | 24
26 | Paper introduction part 2 | Task | 24
27 | Paper methods part 1 | Task | 24
28 | Paper methods part 2 | Task | 24
29 | Paper methods part 3 | Task | 24
30 | Paper results | Task | 24
31 | Paper discussion & conclusion | Task | 24
32 | Full draft of paper and abstract | Task | 24
33 | Review by Assistant Dean | Task | 24
34 | Review by Associate Dean | Task | 24
35 | Final Presentation | Deliverable | 0
36 | Draft slide deck for presentation | Task | 35
37 | Oral presentation day | Task | 35
38 | Final poster | Task | 35

## WBS-List
Steps to create a Work Breakdown Structure List and Diagram
Step 1: | List your deliverables in separate cells in Row 13 in the Project section starting in column A. Insert more columns after the last deliverable if you need more space.
Step 2: | List the tasks that need to be completed under each deliverable.
Step 3: | Increase the indent on tasks and subtasks. (It makes the lists easier to read.)
Step 4: | Copy the lists of Deliverables and Tasks and paste them in the name column in the Task List section. (You want to create a single column that lists all the deliverables and tasks.)
Step 5: | Give each Deliverable and Task a unique ID number.
Step 6: | Label each Deliverable, Task, and Subtask with the correct type in the type column.
Step 7: | Indicate which deliverables belong to the project, which tasks belong to which deliverable, and which subtasks belong to which task by providing the correct ID for each in the dependent column. See the example below.
Step 8: | Copy the information in the 5 columns of the Task List section WITHOUT THE HEADERS and paste it into the table on the left side of the WBS-Chart sheet. (DON'T PASTE OVER THE HEADERS IN THAT SHEET. THE CHART WON'T WORK IF YOU DO.)
Step 9: | Click Refresh in the top-left corner of the chart. You should see a WBS diagram for your project.
Project Name |  |  |  | Task List
Objective 1 | Objective 2 | Objective 3 | Objective 4 | id | name | type | dependent | blank
Deliverable 1 | Deliverable 4 | Deliverable 7 | Deliverable 8 | 0 | Project Name | Project
Deliverable 2 | Task 4 |  | Deliverable 9 | 1 | Objective 1 | Objective | 0
Task 1 | Task 5 |  |  | 2 | Deliverable 1 | Deliverable | 1
Task 2 | Task 6 |  |  | 3 | Deliverable 2 | Deliverable | 1
Task 3 | Deliverable 5 |  |  | 4 | Task 1 | Task | 3
Deliverable 3 | Deliverable 6 |  |  | 5 | Task 2 | Task | 3
|  |  |  | 6 | Task 3 | Task | 3
|  |  |  | 7 | Deliverable 3 | Deliverable | 1
|  |  |  | 8 | Objective 2 | Objective | 0
|  |  |  | 9 | Deliverable 4 | Deliverable | 8
|  |  |  | 10 | Task 4 | Task | 9
|  |  |  | 11 | Task 5 | Task | 9
|  |  |  | 12 | Task 6 | Task | 9
|  |  |  | 13 | Deliverable 5 | Deliverable | 8
|  |  |  | 14 | Deliverable 6 | Deliverable | 8
|  |  |  | 15 | Objective 3 | Objective | 0
|  |  |  | 16 | Deliverable 7 | Deliverable | 15
|  |  |  | 17 | Objective 4 | Objective | 0
|  |  |  | 18 | Deliverable 8 | Deliverable | 17
|  |  |  | 19 | Deliverable 9 | Deliverable | 17

## WBS-Diagram
Employee ID | Name | Title | Manager ID | Role Type | Some Visio diagrams are available for use in Excel. They can be added by going to Insert - Get Add-ins - Search for "Visio" - Click Add next to Microsoft Visio Data Visualizer
0 | Project Name | Project |  |  | Once you've added the Visio Add-in, you can add a chart in a new blank sheet by going to Insert - My Add-ins - Microsoft Visio Data Visualizer - Select the chart you want - Click Create
1 | Objective 1 | Objective | 0 |  | A chart and data table will be added to the blank sheet. Paste the data needed into the data table. (DON'T PASTE OVER THE TABLE HEADERS. THE CHART WON'T WORK IF YOU DO.)
2 | Deliverable 1 | Deliverable | 1 |  | If you run into problems, create a new blank sheet and start fresh. Get help if you can't figure it out.
3 | Deliverable 2 | Deliverable | 1 |  | You can't edit any aspects of the chart except the underlying data unless you have a Microsoft Visio license.
4 | Task 1 | Task | 3
5 | Task 2 | Task | 3
6 | Task 3 | Task | 3
7 | Deliverable 3 | Deliverable | 1
8 | Objective 2 | Objective | 0
9 | Deliverable 4 | Deliverable | 8
10 | Task 4 | Task | 9
11 | Task 5 | Task | 9
12 | Task 6 | Task | 9
13 | Deliverable 5 | Deliverable | 8
14 | Deliverable 6 | Deliverable | 8
15 | Objective 3 | Objective | 0
16 | Deliverable 7 | Deliverable | 15
17 | Objective 4 | Objective | 0
18 | Deliverable 8 | Deliverable | 17
19 | Deliverable 9 | Deliverable | 17

## TaskGanttExample
Project Summary Information
Overall start date: |  | 2023-03-27 | Overall task count: |  | 30 | Filtered task count: |  | 30
Overall end date: |  | 2024-04-26 | Completed task count: |  | 2 | Filtered completed task count: |  | 2
Filtered start date: |  | 2023-03-27 | Incomplete task count: |  | 28 | Filtered incomplete task count: |  | 28
Filtered end date: |  | 2024-04-26
Overall work days: |  | 264 | Overall beginning task work days: |  | 137 | Overall remaining task workdays: |  | 127.1
Overall calendar days: |  | 397
Filtered work days: |  | 264 | Filtered beginning task work days: |  | 137 | Filtered remaining task work days: |  | 127.1
Filtered calendar days: |  | 397
Today:
Planned work:
Actual work:
Next ID #: |  | 31
Date: | time axis 2023-03-27 to 2024-04-29
ID | Task Short Description | Task Notes | Task Group | Assignee | Due Date | Status | Percent Complete | Independent Start Date | Independent End Date | Dependency ID | Dependency Type | Dependency Lag Days | Planned Workdays | Planned Remaining | Planned Start | Planned End | Actual Start | Actual End | Actual Workdays | time axis 2023-03-27 to 2024-04-29
1 | Forward one | Start from the beginning of the project. | Forward Example |  |  | Completed | 100% | 2023-04-14 |  |  |  |  | 2 | 0 | 2023-04-14 | 2023-04-17
2 | Forward two |  | Forward Example |  | 2023-03-23 | In Progress - At Risk | 30% |  |  | 1 | FS | 1 | 3 | 2.1 | 2023-04-19 | 2023-04-21
3 | Forward three |  | Forward Example |  |  | Not Started |  |  |  | 2 | FS |  | 4 | 4 | 2023-04-24 | 2023-04-27
4 | Backward one | Start from the end of the project. | Backward Example |  |  | Not Started |  |  | 2023-04-14 |  |  |  | 2 | 2 | 2023-04-13 | 2023-04-14
5 | Backward two |  | Backward Example |  |  | Not Started |  |  |  | 4 | SF |  | 3 | 3 | 2023-04-10 | 2023-04-12
6 | Backward three |  | Backward Example |  |  | Blocked | 50% |  |  | 5 | SF |  | 4 | 2 | 2023-04-04 | 2023-04-07
7 | Backward four |  | Backward Example |  |  | Completed | 100% |  |  | 6 | SF | -1 | 5 | 0 | 2023-03-27 | 2023-03-31
8 | Prepare project kickoff meeting agenda |  | Project |  |  |  |  | 2023-09-04 |  |  | FS |  | 5 | 5 | 2023-09-04 | 2023-09-08
9 | Questions and keywords for literature review |  | Proposal | [6 empty] | 8 | FS | 5 | 5 | 5 | 2023-09-18 | 2023-09-22
10 | Project Plan Draft |  | Proposal | [6 empty] | 9 | FS |  | 5 | 5 | 2023-09-25 | 2023-09-29
11 | Table of Evidence - initial |  | Proposal | [6 empty] | 10 | FS |  | 5 | 5 | 2023-10-02 | 2023-10-06
12 | Problem Statement, Aim, Objectives |  | Proposal | [6 empty] | 11 | FS |  | 5 | 5 | 2023-10-16 | 2023-10-20
13 | Framework for project planning |  | Proposal | [6 empty] | 12 | FS |  | 5 | 5 | 2023-10-23 | 2023-10-27
14 | Project methods |  | Proposal | [6 empty] | 13 | FS |  | 5 | 5 | 2023-10-30 | 2023-11-03
15 | Project timeline |  | Proposal | [6 empty] | 14 | FS |  | 5 | 5 | 2023-11-06 | 2023-11-10
16 | Project plan final |  | Proposal | [6 empty] | 15 | FS |  | 5 | 5 | 2023-11-13 | 2023-11-17
17 | Project plan revision |  | Proposal | [6 empty] | 16 | FS |  | 5 | 5 | 2023-11-20 | 2023-11-28
18 | Paper introduction part 1 |  | Paper |  |  |  |  | 2024-01-08 |  |  | FS |  | 5 | 5 | 2024-01-08 | 2024-01-12
19 | Paper introduction part 2 |  | Paper | [6 empty] | 18 | FS |  | 5 | 5 | 2024-01-16 | 2024-01-22
20 | Paper methods part 1 |  | Paper | [6 empty] | 19 | FS | -1 | 5 | 5 | 2024-01-22 | 2024-01-26
21 | Paper methods part 2 |  | Paper | [6 empty] | 20 | FS |  | 5 | 5 | 2024-01-29 | 2024-02-02
22 | Paper methods part 3 |  | Paper | [6 empty] | 21 | FS |  | 5 | 5 | 2024-02-05 | 2024-02-09
23 | Paper results |  | Paper | [6 empty] | 22 | FS | 5 | 5 | 5 | 2024-02-20 | 2024-02-26
24 | Paper discussion & conclusion |  | Paper | [6 empty] | 23 | FS | 5 | 5 | 5 | 2024-03-12 | 2024-03-18
25 | Full draft of paper and abstract |  | Paper | [6 empty] | 24 | FS |  | 5 | 5 | 2024-03-19 | 2024-03-25
26 | Draft slide deck for presentation |  | Presentation | [6 empty] | 25 | FS |  | 5 | 5 | 2024-03-26 | 2024-04-01
27 | Oral presentation day |  | Presentation | [6 empty] | 26 | FS |  | 5 | 5 | 2024-04-02 | 2024-04-08
28 | Final paper for review by specialty track director & assistant dean |  | Paper | [6 empty] | 25 | FS | 10 | 5 | 5 | 2024-04-09 | 2024-04-15
29 | Final paper for review by Associate Dean |  | Paper | [6 empty] | 28 | FS |  | 5 | 5 | 2024-04-16 | 2024-04-22
30 | Final poster |  | Presentation | [6 empty] | 27 | FS | 10 | 4 | 4 | 2024-04-23 | 2024-04-26
Note on M19: Christopher Macintosh: There are four dependency types available. The first letter in the dependency type codes refers to the other task. The second letter refers to this task. Available Dependency Types: FS - Finish-to-Start (Forward) [Other task finishes before this task starts.] SS - Start-to-Start (Forward) [Both tasks start at the same time.] SF - Start-to-Finish (Backward) [Other task starts after this task finishes.] FF - Finish-to-Finish (Backward) [Both tasks finish at the same time.]
Note on N19: Christopher Macintosh: The dependency lag allows you change the start time of the next task. Positive numbers will push the start date further into the future. Negative numbers will move the start date in the opposite direction. Example: 1 - delays the start date by one day -1 - moves the start day one day sooner

## TaskGanttBlank
Project Summary Information
Overall start date: |  | 2023-04-14 | Overall task count: |  | 1 | Filtered task count: |  | 1
Overall end date: |  | 2023-04-17 | Completed task count: |  | 0 | Filtered completed task count: |  | 0
Filtered start date: |  | 2023-04-14 | Incomplete task count: |  | 1 | Filtered incomplete task count: |  | 1
Filtered end date: |  | 2023-04-17
Overall work days: |  | 2 | Overall beginning task work days: |  | 2 | Overall remaining task workdays: |  | 2
Overall calendar days: |  | 4
Filtered work days: |  | 2 | Filtered beginning task work days: |  | 2 | Filtered remaining task work days: |  | 2
Filtered calendar days: |  | 4
Today:
Planned work:
Actual work:
Next ID #: |  | 2
Date: | time axis 2023-04-14 to 2024-05-17
ID | Task Short Description | Task Notes | Task Group | Assignee | Due Date | Status | Percent Complete | Independent Start Date | Independent End Date | Dependency ID | Dependency Type | Dependency Lag Days | Planned Workdays | Planned Remaining | Planned Start | Planned End | Actual Start | Actual End | Actual Workdays | time axis 2023-04-14 to 2024-05-17
1 | Task 1 |  | Ob1 - Objective 1 |  |  |  |  | 2023-04-14 |  |  |  |  | 2 | 2 | 2023-04-14 | 2023-04-17
Note on M19: Christopher Macintosh: There are four dependency types available. The first letter in the dependency type codes refers to the other task. The second letter refers to this task. Available Dependency Types: FS - Finish-to-Start (Forward) [Other task finishes before this task starts.] SS - Start-to-Start (Forward) [Both tasks start at the same time.] SF - Start-to-Finish (Backward) [Other task starts after this task finishes.] FF - Finish-to-Finish (Backward) [Both tasks finish at the same time.]
Note on N19: Christopher Macintosh: The dependency lag allows you change the start time of the next task. Positive numbers will push the start date further into the future. Negative numbers will move the start date in the opposite direction. Example: 1 - delays the start date by one day -1 - moves the start day one day sooner

## TasksSummary
Project Phases | Count | Start | End | % Complete | Days Left
Backward Example | 4 | 2023-02-21 | 2023-03-19 | 75% | 7
Backward four | 1 | 2023-02-21 | 2023-02-27 | 100% | 0
Backward three | 1 | 2023-03-01 | 2023-03-13 | 50% | 2
Backward two | 1 | 2023-03-14 | 2023-03-16 |  | 3
Backward one | 1 | 2023-03-17 | 2023-03-19 |  | 2
Forward Example | 3 | 2023-03-19 | 2023-03-30 | 65% | 6.1
Forward one | 1 | 2023-03-19 | 2023-03-20 | 100% | 0
Forward two | 1 | 2023-03-22 | 2023-03-24 | 30% | 2.1
Forward three | 1 | 2023-03-27 | 2023-03-30 |  | 4
Project | 1 | 2023-09-04 | 2023-09-08 |  | 5
Prepare project kickoff meeting agenda | 1 | 2023-09-04 | 2023-09-08 |  | 5
Paper | 19 | 2023-09-18 | 2024-04-22 |  | 95
Questions and keywords for literature review | 1 | 2023-09-18 | 2023-09-22 |  | 5
Project Plan Draft | 1 | 2023-09-25 | 2023-09-29 |  | 5
Table of Evidence - initial | 1 | 2023-10-02 | 2023-10-06 |  | 5
Problem Statement, Aim, Objectives | 1 | 2023-10-16 | 2023-10-20 |  | 5
Framework for project planning | 1 | 2023-10-23 | 2023-10-27 |  | 5
Project methods | 1 | 2023-10-30 | 2023-11-03 |  | 5
Project timeline | 1 | 2023-11-06 | 2023-11-10 |  | 5
Project plan final | 1 | 2023-11-13 | 2023-11-17 |  | 5
Project plan revision | 1 | 2023-11-20 | 2023-11-28 |  | 5
Paper introduction part 1 | 1 | 2024-01-08 | 2024-01-12 |  | 5
Paper introduction part 2 | 1 | 2024-01-16 | 2024-01-22 |  | 5
Paper methods part 1 | 1 | 2024-01-22 | 2024-01-26 |  | 5
Paper methods part 2 | 1 | 2024-01-29 | 2024-02-02 |  | 5
Paper methods part 3 | 1 | 2024-02-05 | 2024-02-09 |  | 5
Paper results | 1 | 2024-02-20 | 2024-02-26 |  | 5
Paper discussion & conclusion | 1 | 2024-03-12 | 2024-03-18 |  | 5
Full draft of paper and abstract | 1 | 2024-03-19 | 2024-03-25 |  | 5
Final paper for review by specialty track director & assistant dean | 1 | 2024-04-09 | 2024-04-15 |  | 5
Final paper for review by Associate Dean | 1 | 2024-04-16 | 2024-04-22 |  | 5
Presentation | 3 | 2024-03-26 | 2024-04-26 |  | 14
Draft slide deck for presentation | 1 | 2024-03-26 | 2024-04-01 |  | 5
Oral presentation day | 1 | 2024-04-02 | 2024-04-08 |  | 5
Final poster | 1 | 2024-04-23 | 2024-04-26 |  | 4
Grand Total | 30 | 2023-02-21 | 2024-04-26 | 70% | 127.1

## Settings
NextID | Status | Assignee | TaskGroup | Holidays
31 | Not Started | me | Ob1 - Objective 1 | 2023-03-05
| In Progress - On Track |  | Ob2 - Objective 2 | 2023-03-06
| In Progress - At Risk |  | Ob3 - Objective 3 | 2023-03-07
| Blocked |  | Ob4 - Objective 4 | 2023-03-08
| Completed |  | Proposal | 2023-03-09
|  |  | Project | 2023-03-10
|  |  | Paper | 2023-03-11
|  |  | Presentation | 2023-03-12
|  |  | Forward Example | 2023-05-29
|  |  | Backward Example | 2023-06-19
2023-07-04
2023-07-24
2023-09-04
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-12-24
2023-12-25
2024-01-01
2024-01-15
2024-02-19
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-05-27
2024-06-19
2024-07-04
2024-07-24

## ProjectPlan
NURS 6880 / 6881 Capstone Project Plan
The purpose of this document is to bring together all the parts of the capstone project plan along with scholarly evidence that describes background information about your project and supports your methods. This is intended to help assess the completeness and suitability of your project plan and help you transition into writing your capstone paper while you work on your project. Citations and references should be in APA format.
Key Information
Important information about your project.
Student Name:
Preceptor Name:
Faculty Name:
Organization hosting the capstone experience:
Setting where the project will take place:
Project Title:
Sponsor(s):
Leader(s):
Team Member(s):
(Click the + / - button to the left to expand / collapse the section.)
Problem – Description
The Available Knowledge section has a broader focus than just describing the local problem. Information in this section should expand on what is written in the Problem Description section and be supported by evidence. Consider the following questions and write about what might be appropriate for your project. What is currently known about the problem in general, including relevant previous studies? Who is affected by the problem? What are the impacts of the problem? How does the problem affect those individuals? When is it a problem? Why is it a problem or why does the problem matter? What are the costs or the other negative impacts of the problem? How prevalent is the problem or how many people are affected? Are there any existing trends that contribute to the problem? Are probable causes of the problem identified? Are there any formal standards related to this problem? Use proper APA citations and references. (Information in this section will become part of the Introduction – Available Knowledge section of your paper.) Address any feedback from previous assignments when you submit your proposal template for subsequent assignments.
(Click the + / - button to the left to expand / collapse the section.)
Problem – Available Knowledge
The Available Knowledge section has a broader focus than just describing the local problem. Information in this section should expand on what is written in the Problem Description section and be supported by evidence. Consider the following questions and write about what might be appropriate for your project. What is currently known about the problem in general, including relevant previous studies? Who is affected by the problem? What are the impacts of the problem? How does the problem affect those individuals? When is it a problem? Why is it a problem or why does the problem matter? What are the costs or the other negative impacts of the problem? How prevalent is the problem or how many people are affected? Are there any existing trends that contribute to the problem? Are probable causes of the problem identified? Are there any formal standards related to this problem? Use proper APA citations and references. (Information in this section will become part of the Introduction – Available Knowledge section of your paper.) Address any feedback from previous assignments when you submit your proposal template for subsequent assignments.
(Click the + / - button to the left to expand / collapse the section.)
Project Aim and Objectives
The project aim is a short statement of the overall purpose of your project. This is a broad statement that will be broken down into smaller objectives. Write your one to two-sentence project aim. Address any feedback from previous assignments when you submit your proposal template for subsequent assignments.
Objectives
Objectives help identify the main steps in your project. They help organize activities to reach the goal identified in your project aim. Write a draft of your project objectives. An objective should consist of a measurable verb (i.e., assess, develop, implement, evaluate) and what you desire to happen. You only need to have as many objectives as is reasonable for the project. Address any feedback from previous assignments when you submit your proposal template for subsequent assignments. Example: Assess parents of adolescents with Type 1 diabetes for their previous use of anticipatory guidance information.
Objective 1:
Objective 2:
Objective 3:
Objective 4:
(Click the + / - button to the left to expand / collapse the section.)
Current Conditions / Context
Describe what the current conditions look like. What is the setting where your project is taking place? (i.e., patients, staffing, system affiliation) You could describe the process currently in use. You might consider creating a diagram or flow chart. Is your capstone project part of a larger project? If so, describe how your project fits with the larger project or meets the goals of the organization. Who are the sponsors, team members, and beneficiaries of your project? Describe who will be directly and indirectly impacted by your project. Describe any contextual factors that may impact the success of your project. (Information in this section will become part of the Methods – Context section of your paper.) Address any feedback from previous assignments when you submit your proposal template for subsequent assignments.
(Click the + / - button to the left to expand / collapse the section.)
Ethical Considerations
Quality improvement projects should follow standard ethical practices in healthcare. Describe any ethical aspects of implementing and studying the intervention(s) and how they were addressed, including, but not limited to, formal ethics review and potential conflict(s) of interest. Some sample text has been provided. Make any changes or additions relevant to your project. Find an article related to ethical considerations in quality improvement relevant to your project and cite it here using a proper APA citation and reference. (Information in this section will become part of the Methods – Ethical Considerations section of your paper.)
(Click the + / - button to the left to expand / collapse the section.)
Rationale / Framework / Model / Theory
Describe the framework/model/theory used to guide the activities of your project. (You may have more than one.) Describe how it aligns with and guides the work on the project. It may be helpful to add a diagram of the framework if one exists. Many quality improvement projects follow the PDSA cycle. Cite relevant literature. You may also discuss any reasons or assumptions that were used to develop the intervention(s), and reasons why the intervention(s) was expected to work. Cite any evidence you may find supports why this type of intervention may work. (Information in this section will become part of the Introduction – Rationale section of your paper.) Address any feedback from previous assignments when you submit your proposal template for subsequent assignments.
(Click the + / - button to the left to expand / collapse the section.)
Objective-Method-Deliverable Table
Use the Objective-Method-Deliverable Table to list your objectives, associated methods, and deliverables (products/outcomes). Project methods should be described using verbs. This is a high-level overview. Specific tasks can be listed later in the Capstone Project Proposal. Deliverables should be described using nouns. What do you plan to produce? Be sure to include an Evaluate objective. (Information in this section will become part of the Methods – Intervention section of your paper.) Address any feedback from previous assignments when you submit your proposal template for subsequent assignments.
Objective |  |  |  | Method(s) |  |  | Deliverable (Product/Outcome)
Will any of your methods or evaluations involve using questionnaires you create or existing instruments? Will you be creating any artifacts as part of your project? (i.e. presentations or documents of some sort) If so, provide the name(s) of existing instruments and cite literature that describes the instrument(s), validity evidence, or psychometric properties. If you're creating a questionnaire or other artifacts, create rough drafts to include as a table, figure, or appendix after the references in this assignment. (Information about the tools or instruments you use will become part of the Methods – Measures section of your paper.)
Analysis
What type of data do you think each questionnaire or instrument will generate? How do you intend to analyze it? (Information about how you intend to analyze your data will become part of the Methods – Analysis section of your paper.)
(Click the + / - button to the left to expand / collapse the section.)
Work Breakdown Structure (WBS)
Information in this section has been adapted from Healthcare Project Management (3rd Edition) (Schwalbe, 2021). A work breakdown structure (WBS) is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project. The WBS is a document that breaks all the work required for the project into discrete deliverables and groups them into a logical hierarchy. The WBS helps put the project team on the same page. If something is missing, it should be added to the WBS. If something additional is added to the WBS which is not intended to be completed as part of this project, it should be removed. A WBS is often depicted in a graphical format, similar to an organizational chart. The name of the entire project is in the top box, called Level 1, and the main groupings for the work are listed in the second tier of boxes called level 2. Additional breakdown can be done with additional levels. One of the main purposes of a WBS is to help breakdown major project deliverables into smaller ones. The WBS should include only the project deliverables and not the tools, techniques, or actions to create those deliverables. The WBS helps you define the deliverables your project should deliver to be successful. One basic method to verify that your WBS is complete is to look at the lowest level of your deliverables and assess if they in combination will give you everything you need to create the higher-level deliverables. Notice that nouns are used to describe the deliverables and not verbs. The main thing to understand is that you’re organizing the main deliverables based on the work that needs to be done and not how the work will be done. The depth at which you decompose a deliverable depends on the complexity of the work, the uniqueness of the work, and the experience of the team. It is good to note the WBS includes the deliverables, but not the detailed characteristics of the deliverables. Specific details of deliverables should be outlined elsewhere. Add a Work Breakdown Structure (WBS) list or diagram with deliverables listed in separate columns and tasks for each deliverable listed in separate rows below their respective deliverable. Plans may not be fully made yet. Just list things as they currently stand.
Project Name
Objective 1 | Objective 2 | Objective 3 | Objective 4
Deliverable 1 | Deliverable 4 | Deliverable 7 | Deliverable 8
Deliverable 2 | Task 4 |  | Deliverable 9
Task 1 | Task 5
Task 2 | Task 6
Task 3 | Deliverable 5
Deliverable 3 | Deliverable 6
(Click the + / - button to the left to expand / collapse the section.)
Project Timeline (Tasks and Due Dates)
Information in this section has been adapted from Healthcare Project Management (3rd Edition) (Schwalbe, 2021). Once the deliverables have been defined in the WBS and the WBS Dictionary, the tasks required to produce each deliverable should be defined. Each task should include the task name and a brief description of the task. It’s often helpful to give each task a number. Additional task attributes may also be defined such as defining task predecessors and task due dates. Defining tasks for deliverables on the WBS should be done from bottom to top on the WBS. Deliverables at lower levels of the WBS should have their tasks defined before deliverables at higher levels since deliverables at higher levels are likely to be composed by combining deliverables from the lower levels. The goal of the task definition process is to ensure that the project team members have an understanding of the work that needs to be done and so the work can be scheduled. It’s good to note at this stage that additional deliverables may be identified and should be added to the WBS. Note that unlike the deliverables described in the WBS, which are listed as nouns, activities are all listed using a verb and then a noun, using verbs such as review, create, develop, interview, write, distribute, and analyze. After defining project tasks, the next step is task sequencing. Task sequencing involves reviewing the task list to determine the relationships or dependencies between tasks. It also involves determining the reasons for dependencies and the different types of dependencies. Some things to consider include if one task needs to be completed before another one can start? Can the project team do several tasks in parallel? Can some tasks overlap? Determining these relationships or dependencies between tasks has a significant impact on developing and managing a project schedule. Once task dependencies have been considered, tasks should be ordered in the sequence in which they need to be accomplished to successfully complete all aspects of the project thereby defining the project timeline. Create a sequenced project timeline in a copy of the TaskGanttBlank sheet of your Capstone Toolkit. Submit the sheet in Canvas.
ID | Task Description (what, how, who) |  |  |  | Dates (to work on task) | Relevant Objective |  | Dependency (task ID or person involved)
(Click the + / - button to the left to expand / collapse the section.)
Follow Up
How will you measure improvement? Will you be using any specific instruments or tools? If so, list the name of the tool and cite any evidence regarding the validity or psychometric properties of the tool. (Information in this section will become part of the Methods - Measures and Methods - Analysis sections of your paper.)
Objective |  | Measure |  |  |  | Analysis
(Click the + / - button to the left to expand / collapse the section.)
References
List your references in APA format here.
(Click the + / - button to the left to expand / collapse the section.)

## HoursLog
Hours Log
Instructions: | Add new hours to the bottom of the table below. We've started for you by adding time for weekly meetings with your project precptor and time to plan and organize the meetings beforehand. (If you don't hold a meeting that week, don't forget to remove the meeting from this list.) Time will be summarized in the HoursSummary sheet, so you don't need to worry about calculating a total. You will use this same workbook to track your practicum hours through both semesters and turn it in each week.
Goal # to reference below | Copy and paste learning goals (LG) and project objectives (PO) here.
LG-1
LG-2
LG-3
PO-1
PO-2
PO-3
Semester | Week | Briefly describe your activities and which goal the activity was related to, if any. | Goal | Time in # of hours
Fall | 4 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 4 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 5 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 5 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 6 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 6 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 7 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 7 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 8 | Spring Break
Fall | 8 | Spring Break
Fall | 9 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 9 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 10 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 10 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 11 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 11 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 12 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 12 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 13 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 13 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 14 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 14 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Fall | 15 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Fall | 15 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 1 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 1 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 2 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 2 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 3 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 3 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 4 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 4 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 5 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 5 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 6 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 6 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 7 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 7 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 8 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 8 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 9 | Spring Break
Spring | 9 | Spring Break
Spring | 10 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 10 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 11 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 11 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 12 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 12 | Weekly meeting with preceptor | Planning & Reporting | 0.5
Spring | 13 | Organizing for meeting with preceptor | Planning & Reporting | 0.5
Spring | 13 | Weekly meeting with preceptor | Planning & Reporting | 0.5

## HoursTotals
Row Labels | Sum of Time in # of hours
Fall | 11
Planning & Reporting | 11
(blank)
Spring | 12
Planning & Reporting | 12
(blank)
Grand Total | 23

## ProgressReports
Project Information
Student Name
Project Name
Preceptor Name
Site Name
Site Location
(Click the + / - button to expand / collapse the section above.)
Fall Week 4 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 5 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 6 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 7 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 8 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 9 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 10 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 11 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 12 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 13 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 14 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Fall Week 15 | Progress Report Final
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 1 | Progress Report (Inlcuding Break)
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 2 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 3 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 4 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 5 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 6 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 7 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 8 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 9 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 10 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 11 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 12 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 13 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 14 | Progress Report
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)
Spring Week 15 | Progress Report Final
Date:
Reporting Period:
Work completed during this reporting period:
Work to complete next reporting period:
What is going well and why?
What is not going well and why?
Suggestions/Issues:
Project changes:
(Click the + / - button to expand / collapse the section above.)

## MeetingAgendas
Project Information
Student Name
Project Name
Preceptor Name
Site Name
Site Location
(Click the + / - button to expand / collapse the section above.)
Fall Week 3 | Project Kickoff Meeting
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
- Introductions - A3 Template Sections - Project title - Project background - Current condition - Aim/Target/Specific Outcome - Root cause - Implementation plan - Is there an existing quality improvement or project framework in use by the organization? (The student should learn what this is.) - Is there any relevant literature related to the project the student should review? - What are the specific project deliverables? - Does the student have any personal learning goals outside of this project? (This is a good opportunity to shadow some individuals and learn more about roles or topics.) - Future meeting schedule? (It's a good idea to set up a meeting schedule at the beginning of the project.)
Action items and due dates for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 4 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 5 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 6 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 7 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 8 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 9 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 10 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 11 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 12 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 13 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 14 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Fall Week 15 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 1 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 2 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 3 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 4 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 5 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 6 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 7 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 8 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 9 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 10 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 11 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 12 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 13 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 14 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)
Spring Week 15 | Project Meeting Agenda/Notes
Meeting Date:
Meeting participants:
Status of action items from last meeting:
Issues/Questions/Concerns/Discussion Items:
Action items for next meeting:
(Click the + / - button to expand / collapse the section above.)

## People
Name | Role | Email | Telephone | Notes

## Searches
Date | Database | Term | Notes
2023-02-10 | https://pubmed.ncbi.nlm.nih.gov/?otool=uutahlib | Does an Insulin Double-Checking Procedure Improve Patient Safety | This pulled up the correct article.
https://scholar.google.com/

## Literature
Reference | Purpose | StudyDesign | SampleSize | Variables | Instruments | Analysis | Findings | Implications | StrengthQuality | Notes
Modic, M. B., Albert, N. M., Sun, Z., Bena, J. F., Yager, C., Cary, T., Corniello, A., Kaser, N., Simon, J., Skowronsky, C., & Kissinger, B. (2016). Does an Insulin Double-Checking Procedure Improve Patient Safety?. The Journal of nursing administration, 46(3), 154–160. https://doi.org/10.1097/NNA.0000000000000314 | determine effectiveness of a double-checking insulin preparation intervention in reducing medication errors | RCT, nonblinded | N = 5238 (266 patients) 1400-bed quaternary care hospital in several units | no errors, wrong dose & prep, wrong dose, wrong time, (See p. 155) | pre-printed cards (designed for study) o self report errors & chart audits | Intent to treat analysis; T tests, chi (p <.05) What is a p? Probability- Statistical significance What is effect size? Magnitude of intervention- Clinical Significance | Predominate error wrong administration time (92%) insulin admin error rate 33.6%--lower in intervention group after controlling for pt characteristics controlling for same nurse insulin with DC no decrease insulin errors | Implications—time saved and pt safety still maintained. Implement practice change is feasible and cost effective and addressed the largest insulin error of mistiming Practice changed (stopped IDC) at Cleveland clin ic due to this study | I-B
Institute for Safe Medication Practices. (2013, June 13). Independent double checks: Undervalued and misused: Selective sse of this strategy can play an important role in medication safety. Retrieved February 10, 2013 from https://www.ismp.org/resources/independent-double-checks-undervalued-and-misused-selective-use-strategy-can-play | Outlines appropriate use of IDC | Expert Opinion | Formal review conducted and adequate | Evidentiary review, expert consensus/opini on |  |  | SMP does not recommend use of IDC for all high-alert meds Avoid sole reliance on IDC | Is IDC necessary or tradition? Other risk- reduction strategies can address the same concerns (barcoding) s IDC truly employed in practice or is primed DC. | V-A

## WritingNotes
Citation | Page | Text | Notes | PaperSection
(Modic et. al., 2016) | 154 | When 2057 insulin errors were assessed over an 18-month period among Pennsylvania healthcare facilities, nearly one-fourth of errors were due to omission, 14% were due to the wrong drugs, and 13% were due to the wrong dose or overdosage.2 Of reported errors, 53% involved elderly patients, and more than 78% of events were those that could contribute to patient harm, specifically labile glucose values. | Good statistics. use this in introduction | introduction

## ChangeLog
These are notes on updates made to the Capstone Toolkit.
Version | Date | Notes
6 | 2023-04-14 | Switched to using a standard name so I can update the document in Canvas without redoing links.